## Data
Project | Inspection_ID | Type of inspection | Day | Starting_time | End time | Duration | Group | Owner notif | Class Notif | Organizer | Organizer phone | Appointment place | Location | Item Inspected | Description
A35 | 000026212011 | Initial | 21/04/2022 | 10:30 | 11:00 | 0:30 | STLO_Steel | W | W | MAREK SZULC |  | Dry dock | B0116 | Water or air testing of tanks | Tightness test of tank 2201 TWW1P, 2101 TWW1S
A35 | 000026211974 | Initial | 21/04/2022 | 11:30 | 12:00 | 0:30 | STLO_Steel | W | W | MAREK SZULC |  | Dry dock | R7626 | Panels junctions, Alignment, Deck plates junction (deck side) | Preparation to welding of UNIT 7626 – deck 5 and shell plate
A35 | 000026211506 | Initial | 21/04/2022 | 12:00 | 12:15 | 0:15 | STLO_Steel | W | W | ARTUR WOZNIAK |  | Dry dock | B0240 | Sections / Sub sections part 00 | Inspection after removed transport equipment on block 240 PS acc. to OPRZ-2100266-240-PP
A35 | 000026211973 | Initial | 21/04/2022 | 08:00 | 08:30 | 0:30 | STLO_Painting | C | - | JAN LUCZEWSKI |  | Crist yard | B0110 | Interior - Full painting system - Calibration | 1st coat (Intershield 300) of B. 110 TT PS Bilge area – DFT insp.
A35 | 000026212008 | Initial | 21/04/2022 | 08:30 | 09:00 | 0:30 | STLO_Painting | W | - | JAN LUCZEWSKI |  | Crist yard | PW3S | Water tanks - First layer if relevant | 1st coat (Interline 975) of PW3S temp. acc. – DFT insp.
A35 | 000026212009 | Initial | 21/04/2022 | 10:00 | 10:30 | 0:30 | STLO_Painting | W | - | JAN LUCZEWSKI |  | Dry dock | PW2S | Water tanks - First layer if relevant | 1st coat (Interline 975) of PW2S prior descaff. – DFT insp.
A35 | 000026211992 | Initial | 21/04/2022 | 10:30 | 11:00 | 0:30 | STLO_Painting | W | - | JAN LUCZEWSKI |  | Crist yard | PW2C | Water tanks - First layer if relevant | 1st coat (Interline 975) of PW2C prior descaff. – DFT insp.
A35 | 000026211917 | Initial | 21/04/2022 | 12:00 | 12:30 | 0:30 | STLO_Painting | C | - | JAN LUCZEWSKI |  | Crist yard | B0110 | Interior - Surface preparation - Calibration | Clean insp. prior 1st coat (Interline 975) of B. 110 SB Flooding Hatches
A35 | 000026212026 | Initial | 21/04/2022 | 12:30 | 13:00 | 0:30 | STLO_Painting | C | - | JAN LUCZEWSKI |  | Crist yard | B0110 | Interior - Surface preparation - Calibration | Clean insp. prior 1st coat (Interlac 786) of B. 110 PS TD Corridor
A35 | 000026212010 | Initial | 21/04/2022 | 13:00 | 13:30 | 0:30 | STLO_Painting | W | - | JAN LUCZEWSKI |  | Crist yard | GWLP | Water tanks - Surface preparation | Clean insp. prior 1st coat (Interline 975) of GWLP
A35 | 000026211948 | Initial | 21/04/2022 | 10:00 | 11:00 | 1:00 | STLO_Outfitting | W | W | IRENEUSZ POPOWSKI |  | Dry dock | B0110 | Insulation in Machinery area | Inspection of thermal 6M insulation on the ceiling in the Pump Room acc. to att. Dwg 12XM100_N4
A35 | 000026211995 | Initial | 21/04/2022 | 09:30 | 10:00 | 0:30 | STLO_Internal | - | - | ANDRZEJ ZLOWOCKI |  | Dry dock | B0114 | Cable trays and trunks | Fitting of cable trays and penetration at LOT 222 (B114) acc. drwg. 501ECO2220 rev. E3 with HV trays preinspection. ONLY
A35 | 000026211993 | Initial | 21/04/2022 | 10:00 | 10:30 | 0:30 | STLO_Internal | - | - | MARCIN SZYMANSKI |  | Dry dock | P6102 | Sections junctions, alignment, deck plates junction | Construction of deck 1 in UNIT joint area 6102-2/6102-1
A35 | 000026211949 | Initial | 21/04/2022 | 11:00 | 11:30 | 0:30 | STLO_Internal | - | - | IRENEUSZ POPOWSKI |  | Dry dock | B0242 | Thin duct : construction and outfitting | Preinspection of VED system on the B242 LOT 411 acc. to att. Dwg 840YSC411_K4 - PANEL STAGE
A35 | 000026211996 | Initial | 21/04/2022 | 11:00 | 11:30 | 0:30 | STLO_Internal | - | - | ANDRZEJ ZLOWOCKI |  | Dry dock | B0114 | Other inspections | PREINSPECTION: Integrity before insulation of ceiling under D0 on the B114 SB (Fore Sewage Pump Room) acc. att. dwg.
A35 | 000026211530 | Settlement remark | 21/04/2022 | 11:00 | 11:30 | 0:30 | STLO_Steel_Baltic | W | W | MATEUSZ KUCINSKI |  | Crist street Czechoslowacka, Gdynia | P2519/2419,B0240 | Blocks junctions (inside and outside part), Alignment | Comments from inspection ID 26210645 EPG 425-772-19-04-2022 2419/2519 (block 240) close white remark no: 100065508, 100065572, 100065538
A35 | 000026211962 | Initial | 21/04/2022 | 10:30 | 11:00 | 0:30 | STLO_Outfitting_Balt | W | W | KACPER SLEPOWRONSKI |  | Crist ul. Czechosłowacka Gdynia | B0236 | Construction,strength,tightness test EXCEPT VFE,VFC,DLC,VFN,FVP (Own:W,Class:W) | Inspection of construction, strength & tightness test - pressure test DNT system - (Block 236 lev A) Air test 0.4 bar. Acc to dwg: a01ttu4130_dnt_Q4
A35 | 000026211914 | Initial | 21/04/2022 | 11:00 | 11:30 | 0:30 | STLO_Outfitting_Balt | W | W | KACPER SLEPOWRONSKI |  | Crist ul. Czechosłowacka Gdynia | B0240 | Construction,strength,tightness test EXCEPT VFE,VFC,DLC,VFN,FVP (Own:W,Class:W) | Inspection of construction, strength & tightness tests - pressure tests EDT system - (Block 240 lev A&B SB) Water test 5.7 bars. Acc to dwg: A01TTU4120_EDT_S4 A01TTU4220_EDT_T4
A35 | 000026211452 | Initial | 21/04/2022 | 09:00 | 09:30 | 0:30 | STLO_Internal_Baltic | - | - | KACPER SLEPOWRONSKI |  | CRIST Stocznia ul. Czechosłowacka Gdynia | B0236/0240 | Thin duct : construction and outfitting | Inspection of AB execusion: AB0000450596 AB0000449216 AB0000445171 AB0000442852 Inspection of AB execusion: AB0000450596 AB0000449216 AB0000445171 AB0000442852
A35 | 000026211494 | Initial | 21/04/2022 | 09:00 | 09:20 | 0:20 | STLO_Internal_Baltic | - | - | MATEUSZ KUCINSKI |  | CRIST ul. Czechosłowacka Gdynia | B0238 | Other inspections | Inspection after welding block 238, lot 432 local 2376 Foundation no: -TRIT1 -UPSIT1 - AC0IT1, MC0IT1 - Technical floor NAVTIS Acc to the dwg :no de plan 000033
A35 | 000026211904 | Initial | 21/04/2022 | 09:15 | 10:00 | 0:45 | STLO_Internal_Baltic | - | - | MATEUSZ KUCINSKI |  | CRIST ul. Czechosłowacka Gdynia | B238/240 | Fire doors installations (including SWT) | Inspection after welding fire doors no block 238/240: 02.0327 F1 02.0168 F6 02.0177 FI1 02.0099 FI1 02.0102 FI1 02.0487 FI8 02.0488 FI8
A35 | 000026211942 | Initial | 21/04/2022 | 09:30 | 10:30 | 1:00 | STLO_Internal_Baltic | - | - | KACPER SLEPOWRONSKI |  | CRIST Stocznia ul. Czechosłowacka Gdynia | L413 | Thin duct : construction and outfitting | Pre-inspection of HVAC systems of deck A, lot 413 board stage (block 236&238) according to drawing: C34_840YSC413_N3 SPEHV0236A_BD_C4 SPEHV0236A_TD_C4 SPEHV0238A_BD_D4 SPEHV0238A_TD_D4
A35 | 000026211923 | Initial | 21/04/2022 | 10:05 | 11:05 | 1:00 | STLO_Internal_Baltic | - | - | MATEUSZ KUCINSKI |  | CRIST ul. Czechosłowacka Gdynia | B0238 | Other inspections | Final pre-inspection of rooms no: -EL 2296 -EL 0830 +EL. Acc. to the sketch
A35 | 000026212004 | Initial | 21/04/2022 | 11:30 | 12:30 | 1:00 | STLO_Internal_Baltic | - | - | KACPER SLEPOWRONSKI |  | Crist ul. Czechosłowacka Gdynia | B0236 | Pipe insulation | Pre-inspection of piping systems insulation – SNT system hot water (Blocks 236 lev A) Scope acc to dwg: A01TTU4130_Q4_SNT Pre-inspection of piping systems insulation – VFE system (Blocks 236&238 lev A) Scope acc to dwg: A01TTU4130_Q4_VFE