## Data
Project | Inspection ID | Type of inspection | Day | Starting time | End time | Duration | Group | Owner notif | Class Notif | Organizer | Organizer phone | Appointment place | Location | Item Inspected | Description
A35 | 000026216248 | Initial | 27/04/2022 | 09:30 | 09:55 | 0:25 | STLO_Steel | W | W | ANGELIKA LAGA |  | G-08-III | P2524-1 | Sections / Sub sections part 00 | Construction of UNIT 2524-1
A35 | 000026216344 | Settlement remark | 27/04/2022 | 09:55 | 10:00 | 0:05 | STLO_Steel | W | W | ANGELIKA LAGA |  | - | P2524-2 | Sections / Sub sections part 00 | Execution of DNV remark from ID26213845
A35 | 000026216229 | Initial | 27/04/2022 | 10:00 | 10:20 | 0:20 | STLO_Steel | W | W | MARCIN SZYMANSKI |  | Dry dock | P6302 | Panels junctions, Alignment, Deck plates junction (deck side) | Construction of UNIT joint 6302-1/6302-2 after welding
A35 | 000026216249 | Settlement remark | 27/04/2022 | 10:20 | 10:40 | 0:20 | STLO_Steel | W | W | MARCIN SZYMANSKI |  | - |  | Panels junctions, Alignment, Deck plates junction (deck side) | Execution of RCG remark from ID26115141
A35 | 000026216226 | Initial | 27/04/2022 | 08:15 | 08:30 | 0:15 | STLO_Painting | C | - | JAN LUCZEWSKI |  | Crist yard | B0110 | Interior - Full painting system - Calibration | 1st coat (Interline 975) of Vent duct B. 110 TD PS – DFT insp.
A35 | 000026216227 | Initial | 27/04/2022 | 08:30 | 09:00 | 0:30 | STLO_Painting | C | - | JAN LUCZEWSKI |  | Crist yard | B0112 | Interior - Full painting system - Calibration | 1st coat (Interline 975) of Cofferdam of B. 112 – DFT insp.
A35 | 000026215670 | Initial | 27/04/2022 | 09:00 | 09:30 | 0:30 | STLO_Painting | W | - | JAN LUCZEWSKI |  | Crist yard |  | Water tanks - First layer if relevant | 1st coat (Interline 975) of PW2S after descaff. – DFT insp.
A35 | 000026216342 | Initial | 27/04/2022 | 09:00 | 09:30 | 0:30 | STLO_Painting | C | - | JAN LUCZEWSKI |  | Crist yard |  | Interior - Full painting system - Calibration | Surface preparation insp. prior 1st coat ( )of Linen store (tank top PS) and LB bilges - calibration
A35 | 000026215671 | Initial | 27/04/2022 | 09:00 | 09:30 | 0:30 | STLO_Painting | C | - | JAN LUCZEWSKI |  | Crist yard | B0112 | Interior - Surface preparation - Calibration | Surface preparation insp. prior 1st coat (Interline 975) of Cofferdam PS TANK TOP block 112
A35 | 000026216420 | Initial | 27/04/2022 | 09:30 | 10:00 | 0:30 | STLO_Painting | W | - | JAN LUCZEWSKI |  | Crist yard | RPW2C | Water tanks - First layer if relevant | 1st coat (Interline 975) of PW2C after descaff. – DFT insp.
A35 | 000026216228 | Initial | 27/04/2022 | 13:00 | 13:30 | 0:30 | STLO_Painting | W | - | JAN LUCZEWSKI |  | Crist yard | RDT5 | Dry tanks - Surface preparation | DFT inspection in DT5
A35 | 000026216250 | Initial | 27/04/2022 | 09:00 | 10:00 | 1:00 | STLO_Outfitting | W | R | IRENEUSZ POPOWSKI |  | Dry dock |  | Shell doors - Hydraulic system | Inspection – preparation to welding of shell door 202 acc. to att. dwg 000C69PBOR_G4
A35 | 000026216329 | Initial | 27/04/2022 | 10:00 | 10:30 | 0:30 | STLO_Outfitting | W | - | IRENEUSZ POPOWSKI |  | Dry dock | B0110 | Thin duct : construction and outfitting | Inspection of VEE system on the B110 (pump room) acc. to att. Dwg 992JP1081_revD4
A35 | 000026216230 | Initial | 27/04/2022 | 11:00 | 12:00 | 1:00 | STLO_Outfitting | W | W | PAWEL STUBBA |  | Dry dock | B0242 | Other heavy equipment | Outfitting of anchor chain chambers and chain locker on the B242 acc. to 212A101_L3
A35 | 000026215696 | Initial | 27/04/2022 | 09:00 | 09:30 | 0:30 | STLO_Internal | - | - | ANDRZEJ ZLOWOCKI |  | Dry dock | B0116 | Other inspections | PREINSPECTION: Integrity before insulation of bulkhead fr. 328 at B116 D0 acc. att. dwg.
A35 | 000026216559 | Initial | 27/04/2022 | 10:15 | 10:30 | 0:15 | STLO_Internal | - | - | IRENEUSZ POPOWSKI |  | Dry dock | B0110 | Other inspections | Execution of AB0000443858
A35 | 000026216558 | Initial | 27/04/2022 | 10:30 | 11:00 | 0:30 | STLO_Internal | - | - | IRENEUSZ POPOWSKI |  | Dry dock | B0602 | Watertight subdivision doors | Preinspection of Watertight door WTD-001 acc. to dwg 273A001 – before welding
A35 | 000026216328 | Initial | 27/04/2022 | 11:30 | 12:00 | 0:30 | STLO_Internal | - | - | PAWEL STUBBA |  | Dry dock |  | Other inspections | Execution of AB0000452055
A35 | 000026216345 | Initial | 27/04/2022 | 13:00 | 14:00 | 1:00 | STLO_Internal | - | - | PAWEL STUBBA |  | Dry dock | RWB1 | Inspection of other tanks before surface preparation | Preinspection - Outfitting & pipe systems in tank WB1 (6001) ACC. TO HABCAP6001rev.B4
A35 | 000026215672 | Initial | 27/04/2022 | 13:20 | 13:40 | 0:20 | STLO_Internal | - | - | ARTUR WOZNIAK |  | Dry dock | P6302 | Sections junctions, alignment, deck plates junction | Construction of UNIT joint 6302-2/6302-3 after welding with change card N-071-6302 rev A
A35 | 000026215689 | Initial | 27/04/2022 | 09:00 | 10:00 | 1:00 | STLO_Outfitting_Balt | W | W | KACPER SLEPOWRONSKI |  | Crist ul. Czechosłowacka Gdynia | B0240 | Construction,strength,tightness test EXCEPT VFE,VFC,DLC,VFN,FVP (Own:W,Class:W) | Inspection of construction, strength & tightness tests - pressure tests VFE&SNT system: - VFE - Block 240 lev B: line no 211P00&261P00 238P00&288P00 239P00&289P00 - SNT Block 240 SB&PS lev B Water pressure test 11 bars. Acc to dwg: A01TTU4220_SNT_T4 A01TTU4220_VFE_T4
A35 | 000026213898 | Initial | 27/04/2022 | 09:00 | 09:30 | 0:30 | STLO_Outfitting_Balt | W | W | MATEUSZ KUCINSKI |  | CRIST dry dock | B236/240 | Fire doors (mechanical / functional test) | Pre-inspection after welding fire doors no (block 236/240): 02.0306 F2 02.0175 FI6 02.0176 FI1 02.0320 FI1 02.0341 FI1
A35 | 000026215687 | Initial | 27/04/2022 | 10:00 | 10:30 | 0:30 | STLO_Internal_Baltic | - | - | KACPER SLEPOWRONSKI |  | CRIST Stocznia ul. Czechosłowacka Gdynia | L413 | Prefabricated pipes | Pre-inspection of piping systems of deck A, lot 413 board stage (blocks 236&238 junction area) VFE, SNT, QAB, VFC, ILT, DNT according to drawing: A0ITTU4130_Q4
A35 | 000026216245 | Settlement remark | 27/04/2022 | 10:30 | 10:45 | 0:15 | STLO_Internal_Baltic | - | - | KACPER SLEPOWRONSKI |  | Crist Stocznia ul. Czechosłowacka Gdynia | P2315/2215,B238 | Cable trays and trunks | Reinspection of pre-inspection of cabel trays - block stage (block 238). Remarks settlement: WR ID 100048716 (origin inspection in Calypso - ID 26132102).